## Gantt
|  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
| Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Literature Research | 4 weeks | bar: March 1 to March 4
Conceptualisation | 5 weeks | bar: March 4 to April 8
Concept Presentation | 27.04.
Programming | 5 weeks | bar: May 9 to June 13
Testing | 5 weeks | bar: May 12 to June 16
Table of Content, List of References | 28.06.
Writing | 6 weeks | bar: June 15 to July 20
Submission of Pre-version | 25.07.
Correction | 1 week | bar: August 21
Time Buffer | 2 weeks | bar: August 22 to August 23
Final Submission | 28.08.
Milestone